## Summary
Maintenance compliance 2026 (from the monthly SCTCM reports)
Each month sheet holds the figure reported on that month's SCTCM KPI scorecard. Blue figures are typed in from the reports; this summary is calculated from them.
Month | Sheet | Compliance (month) | Compliance (year to date) | Budget | Last year (month) | YTD shown in the SCTCM report | Source
2026-01-01 | Jan PM | 27.03% | 27.03% | 70% | – | 27% | CBG - SCTCM report January 2026 (Supply chain).pptx, slide 7
2026-02-01 | Feb PM | 55% | 41.02% | 70% | – | 41% | CBG - SCTCM report February 2026 (Supply chain).pptx, slide 8
2026-03-01 | Mar PM | 32% | 38.01% | 70% | – | 38% | CBG - SCTCM report March 2026 (Supply chain).pptx, slide 8
2026-04-01 | Apr PM | 19% | 33.26% | 70% | 7% | 33.3% | CBG - SCTCM report April 2026 (Supply chain).pptx, slide 7
2026-05-01 | May PM | 21% | 30.81% | 70% | 41% | 30.8% | CBG - SCTCM report May 2026 (Supply chain).pptx, slide 7
2026-06-01 | Jun PM | 1% | 25.84% | 70% | 25% | 25.8% | CBG - SCTCM report June 2026 (Supply chain).pptx, slide 7
2026-07-01 | Jul PM | 37% | 27.43% | 70% | 35% | 27.4% | CBG - SCTCM report July 2026 (Supply chain).pptx, slide 8
2026-08-01 | Aug PM | 54% | 30.75% | 70% | 36% | 30.8% | CBG - SCTCM report August 2026 (Supply chain).pptx, slide 7 (scorecard picture)
Year to date is the average of the monthly figures, the same way the SCTCM reports calculate it (the "YTD shown" column is there to check against).
August is also in Finished PM Compliance.xlsx as 53.7% (the same result before rounding); with both uploaded the dashboards may show either.

## Jan PM
PM'S PLANNED
2026-01-01
EQUIPMENT | % | Budget
% COMPLETION | 27.03% | 70%
Overall planned maintenance completion for January 2026, as reported on the KPI scorecard of CBG - SCTCM report January 2026 (Supply chain). Figure by equipment is not in the report.
Note on B7: Maintenance Compliance, January 2026, from the SCTCM report (slide 7).

## Feb PM
PM'S PLANNED
2026-02-01
EQUIPMENT | % | Budget
% COMPLETION | 55% | 70%
Overall planned maintenance completion for February 2026, as reported on the KPI scorecard of CBG - SCTCM report February 2026 (Supply chain). Figure by equipment is not in the report.
Note on B7: Maintenance Compliance, February 2026, from the SCTCM report (slide 8).

## Mar PM
PM'S PLANNED
2026-03-01
EQUIPMENT | % | Budget
% COMPLETION | 32% | 70%
Overall planned maintenance completion for March 2026, as reported on the KPI scorecard of CBG - SCTCM report March 2026 (Supply chain). Figure by equipment is not in the report.
Note on B7: Maintenance Compliance, March 2026, from the SCTCM report (slide 8).

## Apr PM
PM'S PLANNED
2026-04-01
EQUIPMENT | % | Budget
% COMPLETION | 19% | 70%
Overall planned maintenance completion for April 2026, as reported on the KPI scorecard of CBG - SCTCM report April 2026 (Supply chain). Figure by equipment is not in the report.
Note on B7: Maintenance Compliance, April 2026, from the SCTCM report (slide 7).

## May PM
PM'S PLANNED
2026-05-01
EQUIPMENT | % | Budget
% COMPLETION | 21% | 70%
Overall planned maintenance completion for May 2026, as reported on the KPI scorecard of CBG - SCTCM report May 2026 (Supply chain). Figure by equipment is not in the report.
Note on B7: Maintenance Compliance, May 2026, from the SCTCM report (slide 7).

## Jun PM
PM'S PLANNED
2026-06-01
EQUIPMENT | % | Budget
% COMPLETION | 1% | 70%
Overall planned maintenance completion for June 2026, as reported on the KPI scorecard of CBG - SCTCM report June 2026 (Supply chain). Figure by equipment is not in the report.
Note on B7: Maintenance Compliance, June 2026, from the SCTCM report (slide 7).

## Jul PM
PM'S PLANNED
2026-07-01
EQUIPMENT | % | Budget
% COMPLETION | 37% | 70%
Overall planned maintenance completion for July 2026, as reported on the KPI scorecard of CBG - SCTCM report July 2026 (Supply chain). Figure by equipment is not in the report.
Note on B7: Maintenance Compliance, July 2026, from the SCTCM report (slide 8).

## Aug PM
PM'S PLANNED
2026-08-01
EQUIPMENT | % | Budget
% COMPLETION | 54% | 70%
Overall planned maintenance completion for August 2026, as reported on the KPI scorecard of CBG - SCTCM report August 2026 (Supply chain). Figure by equipment is not in the report.
Note on B7: Maintenance Compliance, August 2026, from the SCTCM report (slide 7 (scorecard picture)).